## Blank RACI
RACI Chart (Roles and Responsibilities Matrix)
Process Name / Description: | Describe the process that this RACI addresses
Created On: | Date | Revision: | Date last revised
Created by: | Note all team members/functions who developed and agreed to this RACI
| Function A | Function B | Function C | Function D | Function E
First Responsibility
Second…
Third…
Fourth…
Fifth…
Sixth…
R = Responsible, A = Accountable, C = Consulted, I = Informed

## Example
RACI Chart (Roles and Responsibilities Matrix)
Process Name / Description: | Plant maintenance project: Repair and resurface plant parking lot during plant shutdown in July
Created On: | 1912-01-01 | Revision: | 2012-04-01
Created by: | Kelly Bradley (facilities mgr), Mike Cole (plant manager), Joe Pallino (HR), Brian Sullivan (security), Billy Ownens (project manager)
| Facilities Mgr | Plant Mgr | HR | Security | Project Mgr
Identify a minimum of three asphalt contractors from Angie's List | C | - | - | - | R
Arrange for contractor visits and quotes | I | - | - | - | R
Review quotes and references, make contractor selection | A | I | I | - | R
Review and finalize contract, lock in plant shutdown week | I | I | - | - | R
Communicate project to shutdown maintenance crew, make sure all vehicles are removed from the lot | I | I | R | I | I
Provide security gate access codes for asphalt crew by June 15 | I | - | A | R | I
Oversee the project during the plant shutdown week, ensure it is completed on time | A | I | I | - | R
R = Responsible, A = Accountable, C = Consulted, I = Informed